## status_report
				Effort Man Days			Schedule
Project	Task ID	Task Stage	Sub-Task	Description	Planned	Updated Planned	Actual	Planned Start	Planned Finish	Actual Start/Estimated Start	Actual/ Estimated Finish	Status (%)	Remarks
Stack 2.0 Validation	1				56.0	56.0	31.5	17-Feb-2014	18-Apr-2014	17-Feb-2014	18-Apr-2014	56.3
Stack 2.0 Validation	1.1	INTVAL	Linux_MN	Validation through MN test specifications(V0.0.4)	18	18	11	17-Feb-2014	12-Mar-2014	17-Feb-2014	12-Mar-2014	61.1
Stack 2.0 Validation	1.2	INTVAL	Altera_CN	Validation through CN test specifications( Testing Procedure_V0.0.2)	5	5	5	18-Mar-2014	25-Mar-2014	18-Mar-2014	25-Mar-2014	100.0
Stack 2.0 Validation	1.3	INTVAL	Xilinx_CN	Validation through CN test specifications( Testing Procedure_V0.0.2)	5	5	2	18-Mar-2014	25-Mar-2014	18-Mar-2014	25-Mar-2014	40.0
Stack 2.0 Validation	1.4	INTVAL	Altera_MN	Validation through MN test specifications(V0.0.4)	10	10	10	25-Mar-2014	07-Apr-2014	25-Mar-2014	07-Apr-2014	100.0
Stack 2.0 Validation	1.5	INTVAL	Linux_CN	Validation through CN test specifications( Testing Procedure_V0.0.2)	5	5	0.5	08-Apr-2014	14-Apr-2014	08-Apr-2014	14-Apr-2014	10.0
Stack 2.0 Validation	1.6	INTVAL	Windows_MN	Validation through basic MN test cases	2	2	0.5	15-Apr-2014	16-Apr-2014	15-Apr-2014	16-Apr-2014	25.0
Stack 2.0 Validation	1.7	INTVAL	Windows_CN	Validation through basic CN test cases	2	2	0.5	17-Apr-2014	18-Apr-2014	17-Apr-2014	18-Apr-2014	25.0
Stack 2.0 Validation	1.8	SPEC	Test Reports and document update	Test Report preparation and document update with newer identified test cases	4	4	1	17-Feb-2014	18-Apr-2014	17-Feb-2014	18-Apr-2014	25.0
Stack 2.0 Validation	1.9	SPEC	Project planning and Controlling	Planning and discussions	5	5	1	17-Feb-2014	18-Apr-2014	17-Feb-2014	18-Apr-2014	20.0

## bug_report
S.NO	BUG ID Kalycito	Version	Priority	Severity	Bug_Status	Platform	Bug Description	Error Log	Assigned To	Reporter	Resolution
1	1209	2.0.0-b1			Open	Linux_MN	Compilation bugs occured when the compiler flag is set to 0xFFFFFFFFFL	stack/src/kernel/pdo/pdok.c:179: undefined reference to `EplGetOplkErrorStr'
2	1211	2.0.0-b1			Closed	Linux_MN	Compile & build the release package in i686 processor causes error	CMake Error at proj/linux/liboplkmn/CMakeLists.txt:64 (MESSAGE): / Unsupported CMAKE_SYSTEM_PROCESSOR i686			18/2/14 / Added i686 in stack
3	1213	2.0.0-b1			Closed	Embedded_CN	Bug | initParal.presActPayloadLimit is wrong	SDO abort code 0x8000021.			03/03/2014 / Changed initParal.presActPayloadLimit to36
4	1217	2.0.0-b1			Open	Linux_MN	Driver compilation on 2.6.31rt linux x86 pc fails	"drivers/linux/drv_kernelmod_edrv/build/src/main.c: / In function ‘powerlinkOpen’: /drivers/linux/ / drv_kernelmod_edrv/build/src/main.c:280: error: / implicit declaration of function ‘init_timer’ drivers/ / Linux/drv_kernelmod_edrv/build/src/main.c: / In function ‘startHeartbeatTimer’:
5	1218	2.0.0-b1			Closed	Linux_MN	Cmake 2.8.0v not installing debug Stack libraries	Cmake error yet liboplkmn/cmake-install.cmake / File INSTALL cannot find liboplkmn.a			06/03/2014 / Increased cmake to v 2.8.7
6	1220	2.0.0-b1			Open	All MN	Unknown data in Non-Linked Objects
7	1221	2.0.0-b1			Open	Embedded_CN	Configuration Device Boot Test fail	make: *** No rule to make target `program-epcs'. Stop.
8	1222	2.0.0-b1			Open	Linux_CN	Linux_Cn_basic run failing	Kernel stack has gone!Exiting / Stack in state off.Shut down kernel stack
9	1224	2.0.0-b1			Open	Windows MN	Qt app fail to run when restarted in Windows MN	Initialisation of powerlink stack failed. / Error code 0x8
10	1225	2.0.0-b1			Open	Windows MN	Windows robustness test fail
11	1226	2.0.0-b1			Open	Windows MN	QT_reset in windows when min and maximised in windows XP
12	1227	2.0.0-b1			Open	All MN	Garbage value in non-used buffer in Asnd farme
13		2.0.0-b1			Open	Altera_MN_dual design	Packet location change in Tx and Rx buffer location to Local	Warning: System.openmac_0: openmac_0.pktBuf must be connected to an Avalon-MM master
					Closed		Stack with text EPL